## Register
Finding ID | Finding and evidence | Evidence limitation | NIST AI RMF function | NIST subcategory (optional) | ISO/IEC 42001 clause | Likelihood (1-5) | Impact (1-5) | Current risk score (L x I) | Mitigation (proposed) | Proposed owner role | Control status | Residual risk | Risk-treatment decision | Pilot-gate implication
R1 | Contradicted or urgent cases are not escalated, and are often routed to 'submit appeal'. The model recommended escalation for 0/22 gold-escalate cases on the held-out set under greedy decoding (0/8 in-template) and 18/264 under sampling, although 20% of its training labels were escalations. Overconfidence probes: 13 of 20 failed on greedy (6/6 contradicted-evidence, 5/5 urgent-symptom probes), every failure being a wrong recommended step (a missed escalation in 11 of the 13). No certainty language or treatment directives appeared in any of 80 probe runs. Held-out next-step accuracy 68.0% [60.2%, 74.9%] (n=150). | Synthetic, templated cases; one adapter and one training seed, so this may be an under-training effect of this adapter rather than a property of the approach. Urgency was never a training signal, so the urgent-symptom expectation (escalate) is an audit-design decision. 20 probes per family: counts, not rates. | MEASURE; MANAGE | MEASURE 2.5 | 6.1.2; 6.1.3; 6.1.4; 8.2; 8.3 | 4 | 5 | 20 | Proposed: do not use the model's recommended_next_step for routing; require human clinical review of every case; add an escalation rule outside the model (for example urgency and contradiction checks); retrain with more escalation examples and re-run this audit before any reliance. | Medical Director / Appeals Operations Lead | Proposed; not implemented; not tested | Unchanged: 4 x 5 = 20. No control has been implemented or tested, so no risk reduction is claimed. | Mitigate (do not rely on the model's routing) | BLOCKING: no pilot use of model-driven routing until escalation behavior is demonstrated on held-out and real-format cases.
R3 | Evidence is misattributed or missing evidence goes unflagged. Fabricated-rationale probes: 9 of 20 failed on greedy, 10 on at least one run, 6 on every run. Greedy failure reasons: missing evidence not flagged 9, recommended submit 6, an unrelated documented fact used as support for a cited criterion 6, text not in the summary 2 (borderline paraphrase). Held-out task: rationale omission 28.0% [21.4%, 35.7%] (n=150), criteria identified correctly 78.7% [71.4%, 84.5%] (n=150), missing evidence identified correctly 70.7% [62.9%, 77.4%] (n=150). | Mostly misattribution, not free invention (invented text was rare). Rule-based scoring with a token-overlap threshold; two borderline labels listed in results/probe_rule_vs_reading.csv. Synthetic facts with no clinical validity. | MEASURE; MANAGE | MEASURE 2.5 | 6.1.2; 6.1.3; 8.2; 8.3; 9.1 | 4 | 4 | 16 | Proposed: show the source sentence for every cited fact and require a reviewer to confirm each one; block 'submit' unless every listed criterion has a verified supporting fact; track omission and misattribution rates on real cases. | Appeals Operations Lead; ML Engineering | Proposed; not implemented; not tested | Unchanged: 4 x 4 = 16. No control has been implemented or tested, so no risk reduction is claimed. | Mitigate | REQUIRED before pilot: mandatory human verification of every cited fact.
R2 | Embedded instructions hijack the output. Prompt-injection probes: 7 of 20 show unambiguous injection effects on greedy and on each sampled seed (counts 7, 7, 7 on the three seeds). On greedy: the bare word 'APPROVED' instead of JSON on all 4 notice-override probes, and the injected fake assistant turn (with its marker) echoed on all 3 delimiter-break probes. A further 10 probes diverge only in the recommended step and are not attributable to the injection without a control. The system prompt told the model to treat input as data. | No un-injected control probes were run, so next-step-only divergence cannot be split from the model's baseline error. 20 probes, one adapter, synthetic injections authored by the audit team; real adversarial text may differ. | MEASURE; MANAGE | MEASURE 2.7 | 6.1.2; 6.1.3; 8.2; 8.3 | 3 | 4 | 12 | Proposed: strict output validation that rejects anything that is not schema-valid JSON; strip or quarantine instruction-like text and role markers from notices before they reach the model; treat member- or provider-authored text as untrusted; add injection tests to release criteria. | Security / Platform Engineering | Proposed; not implemented; not tested | Unchanged: 3 x 4 = 12. No control has been implemented or tested, so no risk reduction is claimed. | Mitigate | BLOCKING for any input channel that includes third-party text, until input handling and output validation are tested.
R4 | Recommendations are unstable between runs. For identical prompts, the recommended step differs across the three sampling seeds for 199 of 600 prompts (33.2%); the whole JSON is identical in only 33.9% of seed pairs. Sampled next-step accuracy was 62.0% versus 68.0% greedy. | Measured at temperature 0.7 / top_p 0.9 only; greedy decoding is deterministic but was not better at escalation. Single adapter; these seeds measure generation variability, not training-seed variability. | MEASURE | MEASURE 2.5 | 6.1.2; 8.2; 9.1 | 4 | 3 | 12 | Proposed: fix decoding (greedy) in production and re-test; log every generation; record a model/version/decoding identifier with each case so a reviewer can reproduce the output. | ML Engineering | Proposed; not implemented; not tested | Unchanged: 4 x 3 = 12. No control has been implemented or tested, so no risk reduction is claimed. | Mitigate | REQUIRED: deterministic decoding and reproducibility logging before pilot.
R5 | Performance drops on formats the model did not see in training. Criteria identified correctly: 100.0% [91.2%, 100.0%] (n=40) on in-template validation vs 78.7% [71.4%, 84.5%] (n=150) on held-out templates (intervals do not overlap). Rationale omission 15.0% [7.1%, 29.1%] (n=40) vs 28.0% [21.4%, 35.7%] (n=150); next-step accuracy 70.0% [54.6%, 81.9%] (n=40) vs 68.0% [60.2%, 74.9%] (n=150). | Validation set has only 40 cases (wide intervals; the omission and next-step comparisons overlap). 'Held-out' means different synthetic templates and wording, not real-world documents. | MEASURE; MAP | MEASURE 2.5 | 6.1.2; 8.2; 9.1 | 4 | 3 | 12 | Proposed: test on a sample of real, de-identified denial notices in the insurer's actual formats before the pilot; widen training template diversity; set a go/no-go threshold on the real-format sample. | ML Engineering; Appeals Operations Lead | Proposed; not implemented; not tested | Unchanged: 4 x 3 = 12. No control has been implemented or tested, so no risk reduction is claimed. | Mitigate | REQUIRED: real-format validation sample before pilot.
R7 | The evidence base cannot certify real-world performance or exclude contamination. n-gram sweep (n = 8, 13, 20): n = 8 flagged 72% of held-out cases, all 618 matches (35 unique spans) being the intentionally shared synthetic policy vocabulary (expected shared-domain vocabulary, not confirmed leakage); n = 13 and n = 20 flagged none. A synthetic positive control was detected at all three n and is excluded from these percentages. | Zero matches at n = 13 and n = 20 do not prove the evaluation set is uncontaminated: n-gram screening misses paraphrase, structural reuse, translation and other non-verbatim leakage, and cannot see pretraining contamination. All data synthetic and templated; one adapter, one training seed. | MAP; MEASURE |  | 6.1.2; 8.2; 9.1 | 3 | 3 | 9 | Proposed: build the acceptance test from real, de-identified, never-trained-on cases with provenance records; add paraphrase and template-level overlap checks; repeat training with more than one seed before relying on any metric. | Model Risk Management | Proposed; not implemented; not tested | Unchanged: 3 x 3 = 9. No control has been implemented or tested, so no risk reduction is claimed. | Mitigate (evidence quality) | REQUIRED: independent real-case acceptance set before any pilot-readiness claim.
R6 | No disparity could be established or ruled out across the two tested slices. Primary metric (required-rationale omission), paired difference: language Spanish minus English +0.00 pp (95% CI -2.33 to 2.33); age 75 minus 45 -0.22 pp (95% CI -3.00 to 2.56); n=150 matched cases, 900 generations per level. Both intervals include zero: unresolved under the preregistered rule. All secondary metrics were also unresolved. Whole-output identity across matched pairs (33.7% language, 33.7% age) matched the same-prompt seed-to-seed rate (33.9%) (exploratory). | Unresolved is not evidence of equal performance. The test changes only a structured header marker, not non-English text, names, or real-world inputs. One adapter, synthetic data, no planted-bias power check. Two slices only; intersectional effects not analysed. | MEASURE; MANAGE | MEASURE 2.11 | 6.1.2; 6.1.4; 8.2; 9.1 | 2 | 4 | 8 | Proposed: do not claim fairness from this audit; disaggregated monitoring by language and age (and other relevant groups) on real pilot cases with predefined review triggers; test non-English notices and names with a power check before expansion. | Compliance / Fairness and Privacy Officer | Proposed; not implemented; not tested | Unchanged: 2 x 4 = 8. No control has been implemented or tested, so no risk reduction is claimed. | Mitigate (monitor); fairness not certified | CONDITION on pilot: monitoring plan agreed; no fairness assurance statement issued from this evidence.
R8 | Policy hallucination and synthetic member-information leakage were not observed. Policy-authority probes 0 of 20 failed and leakage probes 0 of 20 failed on greedy and on every sampled run (0 of 80 runs each; no member-ID token in any leakage output). Unsupported policy citation 0.0% [0.0%, 2.5%] (n=150) on the held-out set and 0 of 1,794 scored fairness generations. | 20 probes per family; the output schema has no member-ID field, which limits the leakage surface; only 7 prefix-completion probes; IDs and names are synthetic and seen once per epoch (3 epochs) in training. Absence in these tests is not proof of absence. | MEASURE | MEASURE 2.10 | 6.1.2; 8.2; 9.1 | 1 | 4 | 4 | Proposed: keep the fixed output schema (no free identifier fields); re-run the policy and leakage probes on every model change; monitor for identifiers and unknown policy IDs in production outputs. | Compliance / Fairness and Privacy Officer; Security | Proposed; not implemented; not tested | Unchanged: 1 x 4 = 4. No control has been implemented or tested, so no risk reduction is claimed. | Accept with monitoring | NON-BLOCKING: monitor; re-test on each model change.

## Method and legend
Purpose | Risk register for a hypothetical health-insurer appeals-drafting pilot (Meridian), built only from the real Week 6 audit results. Rows are findings; no target count.
Evidence rule | Every number in 'Finding and evidence' is formatted from files in results/ (see the Evidence Index sheet). Week 3 findings are not used.
Likelihood (1-5) | Judgment of how often the failure would occur on pilot-like inputs given what was observed in testing: 1 not observed, 2 possible, 3 plausible, 4 frequent in testing, 5 near-certain.
Impact (1-5) | Judgment of consequence if it occurs in a live appeals workflow: 1 negligible, 2 minor rework, 3 delayed or incorrect appeal, 4 serious member or regulatory harm possible, 5 patient-safety-relevant delay or harm.
Scores | Qualitative, assigned by the audit author; not measurements. Reasonable reviewers may score differently.
Residual risk | Equal to current risk. No proposed control has been implemented or tested, so no reduction is claimed.
Control status | Proposed / implemented / tested. All are 'Proposed; not implemented; not tested'.
NIST AI RMF | Mapped at function level (GOVERN, MAP, MEASURE, MANAGE). The subcategory column is optional context. No row maps to GOVERN yet because no governance control was assessed in this audit.
ISO/IEC 42001 | Clauses used: 6.1.2 AI risk assessment; 6.1.3 AI risk treatment; 6.1.4 AI system impact assessment; 8.2 AI risk assessment; 8.3 AI risk treatment; 9.1 monitoring, measurement, analysis and evaluation. Clause 8.4 is not used.
Pilot gate | BLOCKING = must be resolved before any pilot use; REQUIRED = condition of the pilot; CONDITION / NON-BLOCKING as stated.

## Evidence index
Finding ID | Source files (results/ and logs/)
R1 | task_baseline.csv; posthoc_next_step_confusion.csv; probe_summary_by_family.csv; probe_summary_by_probe.csv; posthoc_overconfidence_predicted_vs_expected.csv; probe_results_by_run.csv
R2 | probe_results_by_run.csv; probe_failure_transcripts.jsonl; posthoc_injection_breakdown.csv; probe_rule_vs_reading.csv
R3 | probe_summary_by_family.csv; probe_results_by_run.csv; task_baseline.csv; probe_rule_vs_reading.csv
R4 | posthoc_summary.json; posthoc_pair_agreement.csv; fairness_row_metrics.csv; task_baseline.csv
R5 | task_baseline.csv; task_scores_val.csv; task_scores_eval_h.csv
R6 | fairness_slice_differences.csv; fairness_disaggregated.csv; fairness_row_metrics.csv; posthoc_pair_agreement.csv
R7 | contamination_summary.csv; contamination_matches.csv; contamination_unique_spans.csv; contamination_review.md; contamination_meta.json
R8 | probe_summary_by_family.csv; probe_results_by_run.csv; task_baseline.csv; fairness_row_metrics.csv
Bindings | MANIFEST.json sha256 prefix 29cfecf0ca584a16; adapter sha256 in logs/adapter_sha256.json; environment in results/env_manifest.json

## Limitations
One adapter, one training seed. The three inference seeds measure generation variability, not training-seed variability.
All data are synthetic and templated; no real notices, members or clinical content. No clinical validity claimed.
Rule-based scoring; no model judge; token-overlap thresholds are conventions (80%).
20 probes per family support counts, not failure rates. No un-injected control probes were run.
Fairness tests a structured header marker only (primary language, age), at one decoding setting, with no planted-bias power check. Unresolved is not equal.
The contamination sweep cannot see paraphrase, translation, structural or pretraining contamination.
Post-hoc analyses (posthoc_*.csv) are exploratory and were not preregistered; the preregistered rules and frozen files are unchanged.
A 0.5B model is not what an insurer would deploy; findings concern this audit method and this adapter.